## Bug List
# | Reported Date | Reported By | Severity | Status | Assigned To | Short Description | Expected Result | Actual Result | Steps to Reproduce
1 | 2024-10-07 | Ricky | P2 | Resolved | Ricky | When we fire spells (using M1) it seemingly randomly fires from the top left (0, 0) and goes right | Spells should always have its starting position from the player | Spells would occasionally fire from (0, 0) | Repeatedly cast spells using left click
2 | 2024-10-07 | Ricky | P2 | Resolved | Ricky | If we immediately cast a spell after starting the game, it often does not cast | We should be able to cast spells immediately when the game starts | Spells cannot be immediately cast | Start game and immediately left click to cast spells
3 | 2024-10-08 | Josh | P4 | Resolved | Josh | Projectiles from player to enemies are inconsistent, seems like only when bounding boxes are just barely overlapping | All hits should be registered if bounding boxes are overlapping at all | All casted spell collisions with enemies should be registered | Walk just barely in range of an enemy and cast spells at them
4 | 2024-10-09 | Armin | P1 | Resolved | Armin | Rapidly switching render order | There should be a 'fixed' render order such that they are not rapidly switching render order | Entities frequently change what is rendering on top of each other | Wait until enough entities spawn and overlap on top of each other
5 | 2024-10-11 | Armin | P2 | Resolved | Josh | During damage lock, when the player has taken damge and will be invincible for a short ms, the projectiles pass through it. The projectile correctly doesn't apply damage but it should also disappear | Projectiles should disappear when hitting the player even if they don't take damage | Player doesn't take damage but projectile keeps going | Stand still and allow player to get hit by more than one projectile
6 | 2024-10-11 | Armin | P0 | Resolved | Josh | Crash on Enemy <-> Player collision | Player should not take damage (as of current design) upon collision between player and enemy | Game crashes | Move player into an enemy entity
7 | 2024-11-02 | Josh | P0 | Resolved | Josh | Crashes when player dies | Game should restart without crashing | Game crashes | Player dies and give it time for game to try restarting
8 | 2024-11-02 | Josh | P2 | Resolved | Josh | Lightning and water barrier spells have a much larger bounding box than expected | Bounding boxes should be more accurate to sprite size | The spells are colliding when we don't expect it to since bounding boxes are too large | Turn on debug mode and cast lightning / water spell
9 | 2024-11-02 | Armin | P3 | Resolved | Ben | Keys besides clicking and space bar let us continue from tutorial | Only clicking or space bar should allow us to continue from tutorial | Other keys allow us to continue from tutorial | Use other keys in the tutorial screen
10 | 2024-11-04 | Luca | P3 | Resolved | Luca | Player animation will not reset to movement direction if an attack is triggered while walking | Should briefly change direction for the attack, and then change back to their direction of movement | Stays facing the attack direction (e.g. N) while continuing to move (e.g W) | Move in one direction and attack in another
11 | 2024-11-11 | Josh | P1 | Resolved | Josh | Only one shard of the ice spell applies damage | Any number of ice shards that hits an enemy should be registered to hit damage | Only one shard applies damage | Hit an enemy with more than one ice shard
12 | 2024-11-13 | Luca | P1 | Resolved | Ricky | Player will often automatically move after the game has been restarted | Player should be stationary at game start | Player moves in a seemingly random direction, and will not stop until that key is pressed | Hold movement keys as death timer counts down
13 | 2024-11-17 | Luca | P2 | Resolved | Luca | Blinking after attack animation | Attack animation should transition smoothly back into walk/idle | There is a brief blink changing back, visually distracting | Attack as player or have enemies trigger attack
14 | 2024-11-19 | Ricky | P2 | Resolved | Ricky | Player doesn't face in proper direction when casting | Player faces close to direction of mouse when casting | Player is forced to face right when casting | Cast while not facing right
15 | 2024-11-28 | Ben | P3 | Resolved | Ben | Some combination of inputs (e.g. can't press E while walking) are malfunctioning | Player should be able to walk and press E to heal at the same time | Pressing E to heal doesn't work while the player is walking | Simultaneouly walk and heal using 'E' (when healing is not on cooldown)
16 | 2024-11-28 | Josh | P2 | Resolved | Josh | Enemy projectiles are traveling through the player on-hit instead of being destroyed | Enemy projectile should disappearing when it collides with the player (even if player is invincible) | Enemy projectile is not destroyed on collision with player. Instead, it keeps travelling. | Allow the player to be hit with an enemy projectile
17 | 2024-11-29 | Josh | P2 | Resolved | Ricky | Max level ice spell hits enemies numerous times | The spell should only damage enemies ONCE | The spell damages enemies FIVE times (at most) | Attack enemies using the max level ice spell